## CONTENTS
JLR Way Ref: JLR-HTG-122809 |  | ¦ | Issue Level | 1.7 | ¦ | Author | PBEDDOW1 | ¦ | Issue Date | 2025-03-20 | ¦
| Table Of Contents | Description
| APQP Workbook Summary | Explained key APQP process principles.
| APQP Review Summary PCDS V4 | High level review of APQP reviews.
| PCDS V4 - newAPQP Workbook_V1 | Main Workbook.
| Change Log-newAPQP Workbook | Change Log.
Printed Copies are Uncontrolled

## APQP Workbook Summary
JLR Way Ref: JLR-HTG-122809 | ¦ | Issue Level | 1.7 | ¦ | Author | PBEDDOW1 | ¦ | Issue Date | 2025-03-20 | ¦
Printed Copies are Uncontrolled
New APQP Workbook
Overview
The APQP (Advanced Product Quality Planning) Workbook defines the internal JLR process for working with the supply base to launch quality parts withing the Commodity Creation Delivery System (CCDS).
Process
The process is governed by the following key principles:
Supplier launch success and achievement of PSW is the joint responsibility of the cross-functional Commodity Team.
The Commodity Team will formally evaluate status at minimum of 7 key team reviews.
The 7 meetings are based on clusters of APQP Deliverables that are linked to the CCDS process.
The Commodity Team must meet on a regular basis between the 7 key reviews at frequency to be identified by the team.
Supplier engagement with APQP will begin immediately after sourcing.
The Commodity Team will provide the supplier with as single Jaguar Land Rover voice on all launch matters.
Team engagement will continue until the supplier has successfully completed all APQP requirements and achieved PSW.
Timing for APQP reviews and deliverables is driven by the Commodity Plan and has been agreed by the commodity Team.
How each deliverable is produced and the standard to be met is described in the CCDS processes.
Which Version of APQP workbook should I Use?
New APQP workbook V2, supported by 3DEx system, should be used for all new Programmes following PCDS V4.
Legacy workbooks supported by eAPQP system can be found in JLR-HTG-122809.
Please refer to the CCDS Manual for further information.
(CCDS - APQP Workbook)
(CCD Manual)

## APQP Review Summary PCDS V4
JLR Way Ref: JLR-HTG-122809 | ¦ | Issue Level | 1.7 | ¦ | Author | PBEDDOW1 | ¦ | Issue Date | 2025-03-20 | ¦
*** Additional Information:
1. Information on LRR8:
2. Kindly note - 3DX APQP tool is NOT a document repository tool.
Printed Copies are Uncontrolled

## PCDS V4 - 3DX APQP Workbook_V2
JLR Way Ref: JLR-HTG-122809 |  | ¦ | Issue Level |  | 1.7 | ¦ | Author | Paul Beddow | Issue Date | 2025-03-20
JLR Approval Group | APQP Deliverable No. | APQP Task Title | Activity Description | Evidence Required(CCDS Process Ref) | Master Location(CCDS Process Ref) | Suggested CCDS Process Step Ref (APQP - 3DX Cloud) | Latest Event (PCDS V4 Ref)
Review 1: Phase
Engineering, Procurement | Review 1 | Review 1 | Please review below Tasks 1) JLR Commodity Team is formed 2) The commodity plan is compatible with achieving supplier sourcing timing requirements for the programme 3) Cross functional plan to achieve PSW is reviewed by Lead Engineer and Buyer - by product of having an aligned plan Concurrence Route - PE Engineer + Purchasing Concurrence Review Owner: PE Engineer Evidence Required: None |  |  |  | PSC
Review 2: Phase
Engineering, Procurement | 2.7 & 2.8 | Engineering Specifications & Material Specifications | Supplier has received all necessary Product Design Specification information to plan the design, manufacture and shipment of the product. This is including but not limited to Engineering Statement of Work (ESoW) and Product Design Specification (PDS). | ESoW PDS | JLR Engineering Project Folder | 2.2.9 -Create Product Design Specification (PDS) & Engineering Statement of Work (ESoW) (Enables RFQ P4.3) 4.3.2 - eGSP 4.3.12 -Issue RFQ Pack To Listed Suppliers via Ariba | PSC
Engineering, STA | 2.11 | Special Product And Process Characteristics | All Potential Special Characteristics and any other Critical to Quality (CTQs) have been successfully documented and cascaded by JLR to affected suppliers. | SCSS | JLR Engineering Project Folder | 2.3.4 - Cascade Potential Special Characteristics Yc/Ys (Geba 1) 2.4.6 - Confirm Special Characteristics | PSC
Procurement, STA | A.1 | Capacity planning eCAR | The supplier has received all neccesary volume information from JLR Procurement in order to plan porduction capacity. The Capacity Planning eCAR has been submitted using surrogate data and meets JLR Sourced Volume | Capacity Planning eCAR | eCAR | 7.3.3 - Submit Phase 0 eCAR 7.5.3 -Submit Phase 3 eCAR | FR
Engineering | Review 2 | Review 2 | Please review below Tasks. 1) 2.7 & 2.8 - Engineering Specifications & Material Specifications 2) 2.11 - Special Product And Process Characteristics 3) A.1 - Capacity planning eCAR Review Owner: Product Engineering |  |  |  | FR
Review 3: Phase
Engineering, Procurement | C.1 | Approve and Issue S release order | The Supplier has received the S Release with all required technical content. All Parts have been ordered to support FIS Build (S Release Order). | 3D CAD, 2D Drawing (as agreed), PDS Orders | CAD System, Engineering Project Folder. WERS Release GPIRS | 2.3.9 - Prepare 'S' Release (Where Required) 2.4.11 -Prepare 'S' Release | EDJ
Engineering | Review 3 | Review 3 | Please review below Tasks 1) C.1 - Approve and Issue S release order Review Owner: Product Engineering |  |  |  | EDJ
Review 4: Phase
Engineering | 2.1 | Design Failure Mode and Effects Analysis (DFMEA) | Supplier & JLR DFMEAs have been reviewed and the required actions have been taken to reduce the level of analysed risk to an agreed level. | DFMEA | JLR SCSS Supplier PPAP File | 2.3.1 - Review System Design & System level DFMEA with your interfacing Component owners & Stakeholders 2.4.1 - Review System Design & System Level DFMEA with your interfacing Component owners & stakeholders 2.4.2 - Review Design For Failure Modes 2.5.1 - Final System Design Review with your interfacing Component owners & stakeholders 6.3.15 - | EDC
Engineering | 2.5 | Prototype Build - Control Plan | Part Inspection Plan and Prototype Control Plan has been generated, reviewed by Commodity Team and agreed with JLR Product Engineer | Signed Part Inspection Plan Control Plan | RADs, Supplier | 2.3.8 -Confirm Manufacture for Prototype parts 6.3.7.1 -Will plan deliver to programme requirements? -Escalate via Exception Management process | PR
Engineering, STA | 2.12 | Gauges/Testing Equipment Requirements | Gauges / Testing equipment required for the product have been identified and have a plan to track to completion. | Include in Supplier Delivery Plan | Attach to 3DX APQP plan | 6.4.2 -Confirm capacity plan on planning eCAR 6.4.3 - onfirm process flow | PSC
Engineering, Procurement, STA, MP&L | 2.13 | Team Feasibility Commitment | The suppliers product quality planning team and production management must assess the feasibility of the proposed design at this stage. Note, this requirement must be completed in all situations regardless of whether JLR or the supplier are design responsible. The team must be satisfied that the proposed design can be manufactured, assembled, tested, packaged and delivered in sufficient quantity to schedule. | PDF of Signed Feasibility Commitment | Attach to 3DX APQP plan | 2.4.8 - Prepare For Manufacturer Feasibility Event 2.4.9 - Confirm Feasibility with Manufacturer 2.5.1 - Final System Design Review with your interfacing Component owners & stakeholders | PR
STA | 3.3 | Process Flow Chart | The Manufacturing Process Flow Chart is available and represents the planned production process. | PPAP Checklist Process Flowchart | ePPAP Supplier PPAP File | 6.3.6 -Confirm Commodity Plan (see 2.2.1) 6.3.6.1 - Confirm Commodity Plan (see 2.2.1) 6.3.12 - | PR
STA | 3.4 | Floor Plan Layout | The Floor Plan Layout has been completed | Floor Plann Layout | Supplier | NA | PR
STA | 3.7 | Pre-Launch Control Plan | The Pre-Launch control plan should contain details / descritptions of the dimensional measurements and material and functional tests that will occur after prototype and before full production. The pre-launch control plan should include additional product/process controls to be implemented until the production process is validated. | Pre-Launch Control Plan | Supplier PPAP File | 6.5.2.1 -Confirm plan for Run at Rate | PR
Engineering, Procurement | C.2 | Approve and Issue T release order | The supplier has received the Tooling T Release with all the required information. | 3D CAD, 2D Drawing (as agreed), PDS Orders | CAD System, Engineering Project Folder. WERS Release GPIRS | 2.4.12 -Prepare 'T' Release 4.6.6 -Approve Release Of Purchase Order to Supplier (In Line DoA) (TBSS offshore) | PRC
Engineering, Procurement | C.3 | Approve and Issue P release order | The supplier has received the Production 'P' Release with all the required information that makes up the product design specification. | 3D CAD, 2D Drawing (As agreed), PDS, Completed Release Checklists ASR Team Confirmation Email | CAD System, Engineering Project Folder. WERS Release EBER Hub | 2.5.3 -Prepare 'P' Release 4.7.6 -Approve Release Of Purchase Order to Supplier (In Line DoA) (TBSS offshore) | PRC
Engineering | Review 4 | Review 4 | Please review below Tasks 1) 2.1 - Design Failure Mode and Effects Analysis (DFMEA) 2) 2.5 - Prototype Build - Control Plan 3) 2.12 - Gauges/Testing Equipment Requirements 4) 2.13 - Team Feasibility Commitment 5) 3.3 - Process Flow Chart 6) 3.4 - Floor Plan Layout 7) 3.7 - Pre-Launch Control Plan 8) C.2 - Approve and Issue T release order 9) C.3 - Approve and Issue P release order Review Owner: Product Engineering |  |  |  | PRC
Review 5: Phase
Engineering | 2.3 | Design Verification | Design Verification must be planned and completed confirming the design meets the customer requirements. Confirm that DV testing has been completed and Engineering Sign-Off has been agreed | ESO Document | Attach to 3DX APQP plan | 3.3.1 -Confirm Test Plan Is Active 3.3.5 - Evaluate Results Against Requirements & Associated Target 3.3.8 - Obtain agreement to progress to Engineering Release | SSO
STA | 2.10 | New Equipment Tooling And Facilities Requirements | The Supplier Product Delivery Plan is complete and defines the activities necessary to meet the requirements of JLR APQP and JLR Phased PPAP (including JLR Customer-Specific Requirements). The plan clearly shows the Critical Path including Sub-Supplier activities. It can be completed when all production tooling, manufacturing and measuring equipment has been installed and commissioned at the serial production location. The plan will be available to support PR gateway and must be closed out before Phase 0 Run@Rate (Significant Production Run) | Supplier Delivery Plan Status PDF | Attach to 3DX APQP plan | 6.3.8 -Conduct detailed design of Production and logistic process 6.4.1 -Confirm complete Product Design Record 6.5.1 -Run trial in home line 6.7.2 -Evaluate the PPAP file 6.7.4 - Supplier submits Phase 1/2 PSW & AAR to JLR mailbox (or ePSW) | TT MRD
MP&L | 3.1 | Packaging Standards and Specifications (including initial EU1121) | Supplier understands packaging stategy for parts (Checklist), Fully understands the process and requirements through supplier guidelines. Understand EU1121 process. A plan is in place to ensure production intent packaging used for TT Build events onwards | EU1121 Form (Attached at 4.6) | MP+L Sharepoint | 8.6 -Prepare HTFB Launch Readiness | IPB MRD
MP&L | 3.1a | Buy-off of new special packaging | All new special packaging prototypes for Serial production have been bought off by all functions. | Prototype Buy-off form | AGPE H: Drive | 8.4 - Review Production Packaging | LRR2
STA | 3.6 | Process Failure Mode And Effects Analysis (PFMEA) | The PFMEA is live and is linked to the Manufacturing Process Flowchart, Control Plans (pre-production and production) and Operator Work Instructions. | PFMEA | Supplier PPAP File | 6.5.2.1 -Confirm plan for Run at Rate | TT MRD
STA | 3.8 | Process Instructions | Process Instructions should be available for every stage of the production process and provide sufficient understanding and detail for all personnel who have direct responsiblity for operation of the process. | Process Instructions | Supplier | 6.3.6 - Confirm Commodity Plan (see 2.2.1) 6.3.13.2 - | TT MRD
Procurement, STA, MP&L | A.7 | VSM | Complete Value Stream Map | Value Stream Map Supply Chain Design Dossier (SCDD) | JLR STA Project Folder | 6.3.6 - Confirm Commodity Plan (see 2.2.1) 6.3.13 - Execute Plan (up to P6.4 | TT MRD
Engineering | B.1 | IMDS | IMDS database has been populated with all material constituent data | IMDS Report IMDS System Reference Number | IMDS System Supplier PPAP File | NA | CSO
STA | B.2 | Sub-Suppliers PPAP Plan | Sub-suppliers PPAP plan should be available for review. At each phase of Tier 1 PSW the sub-supplied parts must be at that stage or greater, ie, for Phase 0 Run@Rate at tier 1 all sub-supplied parts must have achieved minimum Phase 0 Run@Rate condition. | Sub-supplier Plan | Supplier | 6.7.2 - Evaluate the PPAP file | TT MRD
STA | Review 5 | Review 5 | Please review below Tasks 1) 2.3 - Design Verification 2) 2.10 - New Equipment Tooling And Facilities Requirements 3) 3.1 - Packaging Standards and Specifications (including initial EU1121) 4) 3.1a - Prototype Packaging 5) 3.6 - Process Failure Mode And Effects Analysis (PFMEA) 6) 3.8 - Process Instructions 7) A.5 - VSM 8) B.1 - IMDS 9) B.2 - Sub-Suppliers PPAP Plan Review Owner: STA |  |  |  | TT MRD
Review 6: Phase
STA | 4.1 | Significant Production Run | Phase 0 PSW Run-at-Rate has been conducted. If applicable, the master sample(s) produced during the Phase 0 Run-at-Rate has been approved by the customer. Phase 0: Run-at-Rate Objectives: To confirm that all production input requirements are available and understood and can support a limited production run. To provide an early indicator that the design of the process/tool/facility has the potential to produce at rate the required number of acceptable parts as determined by the pre-launch control plan. Phase 0 is a limited run-at-rate of parts for at least one production stream, not a demonstration that all PPAP requirements have been met for that production stream. | Phase 0 eCAR submission | eCAR | 6.6.4 - eCAR Approved by STA | TT MRD
STA | 4.2 | Measurement Systems Analysis | The Measurement Systems Analysis (MSA) has been completed for all measuring equipment defined in the Control plan | PPAP Checklist MSA Report | ePPAP Supplier PPAP File | 6.5.3 - Agree date for Run at Rate | TT MRD
STA | 4.3 | Preliminary Process Capability Study | The initial process capability studies for all special characteristics demonstrate stability. | PPAP Checklist Capability Studies | ePPAP Supplier PPAP File | 6.7.2 -Evaluate the PPAP file | TT MRD
Engineering, STA | 4.4 | Production Part Approval | For Phased PPAP status please complete "Phased PPAP & Capacity Planning Section". All parts supplied from PVB onwards must be supported by Phase 1 PSW minimum or an iPSW where PSW requirements have not been met. A PPAP Checklist must be presented in both cases - against each | PPAP Checklist | Supplier PPAP File | 6.7.5 - Repeat processes 6.6 & 6.7 to complete Phase 2 6.7.6 - Proceed to process 6.8 6.7.7 - ePSW 6.7.8 - ePSW 6.7.9 - ePSW 6.8.7 - ePSW 6.8.8 -ePSW | TT MRD
Engineering | 4.5 | Production Validation Testing | PV Testing has been completed and results have been signed-off by JLR Product Engineering | PV Sign-off against PDS Requirements | Attach to 3DX APQP plan | 3.6.7 - 6.7 -Verify input requirements are in place | TT MRD
MP&L | 4.6 | Packaging Evaluation | Packaging trials and tests have been completed to assess the protection of the product from normal transportation damage and adverse environmental factors. The supplier has uploaded packaging information (EU1121) and it has been approved by JLR | EU1121 Form | MP+L Sharepoint | 8.8 -Prepare PP Launch Readiness | TT MRD
STA | 4.7 | Production Control Plan | The Production Control Plan is complete and is linked to the PFMEA, Manufacturing Process Flowchart and Operator Work Instructions | Control Plan | Supplier PPAP File | 6.3.12 -Execute Plan (up to P6.4) | TT MRD
Procurement, STA | A.2 | Phase 0 Run-at-Rate - eCAR submission | The Phase 0 PSW Run-at-Rate eCAR has been submitted and confirms achievement of the required build rate to meet sourced volume | Phase 0 eCAR submission | eCAR | 7.3.3 - Submit Phase 0 eCAR 6.6.3 - Confirm outcome: - Qty parts in planned time period at correct cycle time - Update DFMEA & PFMEA. 6.6.4 -Complete and approve eCAR > 15 shifts | TT MRD
STA | A.3 | Phase 1 Quality Verification | Phase 1 PSW Quality Verification is complete. Phase 1: Quality Verification Utilises parts produced during Phase 0. Objectives: To confirm all customer design record and specification requirements are properly understood by the supplier. To provide an early indicator that the design of the process/tool/facility has the potential to produce product consistently meeting these requirements during an actual production run at the quoted production rate by operating a minimum of one selected production stream. Phase 1 demonstrates that all PPAP requirements have been met for one production stream. | PPAP Checklist Phase 1 PSW | Supplier PPAP Folder | 6.7.7 - Phase 1/2 Approved 6.7.9 - Phase 1/2 Approved | TT MRD
Engineering, STA | B.3 | AAR | Colour, gloss and texture / graining sign-off completed (AAR - Appearance Approval Report) aligned | AAR Report | Supplier PPAP File | 6.7.2 - Evaluate the PPAP file 6.7.7 -Phase 1/2 Approved | TT MRD
Engineering, STA | B.4 | Branding | Compliance to JLR branding directive has been demonstrated on all parts produced during the Phase 0 Run-at-Rate | Parts that satisfy drawing + E108 branding directive or exemption number | Not Applicable | 6.7 -Verify input requirements are in place 6.6.2.3 -Run process at rate | TT MRD
Engineering, STA | D.1 | Part Inspection Plan & Report | Part inspection Plan is applicable for every new tooled end item before tooling, gauges and parts are manufactured. Part Inspection Report is applicable regardless of scalability for all pre-production build phases (M1, VB, IPB) for any supplied part without an approved PSW for PPAP Phase 1. Part Inspection Report should also be supplied to support any iPSW submission if approved Phase 1 PPAP is not available & should be updated at each change in part maturation. | Signed Part Inspection Report | RADs | 6.3.7.1 -Will plan deliver to programme requirements? -Escalate via Exception 6.5 - Industrialise the process | TT MRD
STA | D.2 | Sample Parts from run at rate | All sample parts produced during the Phase 0 Run-at-Rate are confirmed to meet all requirements of the design record and control plan. From the sampled parts 100% of all required measurement points are within tolerance detailed on Part Inspection Report. | PPAP Checklist Measurement Reports | ePPAP Supplier PPAP File | 6.7.2 -Evaluate the PPAP file | TT MRD
Engineering, STA | D.3 | Part Maturity | Provide updated part pedigree of parts till parts fully matured and signed off (are parts off tool only, off tool in home line, off tool at rate...) | Part Maturity Overview | Attach to 3DX APQP plan | NA | J1
Engineering, Procurement, STA, MP&L | E.3 | AIMS | Link any existing unresolved AIMS to APQP Plan by part number by creating an issue to track it in 3DS. | Unresolved AIMS Number | Attach to 3DX APQP plan | NA | TT MRD
Engineering, Procurement, STA, MP&L | E.4 | Support Plan | For any design change required, a new support plan must be attached to the APQP plan for evidence. | Support Plan | Supplier PPAP Folder | NA | TT MRD
STA | Review 6 | Review 6 | Please review below Tasks 1) 4.1-Significant Production Run 2) 4.2-Measurement Systems Analysis 3) 4.3-Preliminary Process Capability Study 4) 4.4-Production Part Approval 5) 4.5-Production Validation Testing 6) 4.6-Packaging Evaluation 7) 4.7-Production Control Plan 8) A.2-Phase 0 Run-at-Rate - eCAR submission 9) A.3-Phase 1 Quality Verification 10) B.3-AAR 11) B.4-Branding 12) D.1-Part Inspection Plan & Report 13) D.2-Sample Parts from run at rate 14) D.3-Part Maturity 15) E.3-AIMS 16) E.4-Support Plan Review Owner: STA |  |  |  | J1
Review 7: Phase
STA | A.4 | Phase 2 Production Verification. | Phase 2 PSW Production Verification is complete - required where more than 1 production stream will be used in the supplier facility to produce the product. Phase 2: Production Verification Objectives: To confirm all customer engineering design record and specification requirements are properly understood by the supplier, and that ALL production streams have the potential to produce product consistently meeting these requirements during an actual production run at the quoted production rate. Phase 2 demonstrates that all PPAP requirements are met for all production streams. | PPAP Checklist Phase 2 PSW | Supplier PPAP Folder | 6.7.7 - Phase 1/2 Approved 6.7.9 - Phase 1/2 Approved | TT MRD
Procurement, STA | A.5 | Phase 3 eCAR for non sequence suppliers | For non-sequenced parts, Phase 3 PSW capacity verification is complete. The Phase 3 eCAR has been submitted and confirms achievement of the sourced volume Phase 3: Capacity Verification Objective: Verify the supplier's production system can support customer declared volume requirements while meeting Phase 2 requirements. | Phase 3 eCAR PPAP Checklist Phase 3 PSW | eCAR Supplier PPAP Folder | 6.8.10 (not sure on non sequence/sequence parts) , 6.8.12 - Phase 3 Approval | PP MRD
Procurement, STA | A.6 | Phase 3 eCAR for sequenced suppliers | For sequenced parts, Phase 3 PSW Capacity Verification is complete and the Phase 3 eCAR has been submitted and confirms achievement of the sourced volume Phase 3: Capacity Verification Objective: Verify the supplier's production system can support customer declared volume requirements while meeting Phase 2 requirements. | Phase 3 eCAR PPAP Checklist Phase 3 PSW | eCAR Supplier PPAP Folder | 6.8.10 (not sure on non sequence/sequence parts) , 6.8.12 - Phase 3 Approval | LRR8
Procurement | B.5 | Commercial PPAP | Commercial validation completed for all core & specialist Commercial PPAP activities | C-PPAP Checklist | C-PPAP System | NA | LRR8
Engineering, STA | E.1 | Alert | If Phase 1 forecast date is past PCDS gateway, supplier must raise a request for alert that can be closed once alert is authorised by Plant Quality. | Alert | WERS Supplier PPAP Folder | 6.8.6 -Submit documentation to JLR mailbox / ePSW | J1
Engineering, STA | E.2 | IPSW | If Phase 1 forecast date is past PCDS gateway, supplier must raise a request for iPSW that can be closed once is signed off by relevant JLR approvers. | iPSW | Supplier PPAP Folder | 6.8.6 -Submit documentation to JLR mailbox / ePSW | J1
STA | Review 7 | Review 7 | Please review below Tasks 1) A.4-Phase 2 Production Verification. 2) A.5-Phase 3 eCAR for non sequence suppliers 3) A.6-Phase 3 eCAR for sequenced suppliers 4) B.5-Commercial PPAP 5) E.1-Alert 6) E.2-IPSW Review Owner: STA |  |  |  | LRR8
Printed Copies are Uncontrolled

## Change Log-newAPQP Workbook
JLR Way Ref: JLR-HTG-122809 |  | ¦ | Issue Level |  | 1.7 | ¦ | Author | PBEDDOW1 | ¦ | Issue Date |  | 2025-03-20 |  | ¦
| Document Name: | JLR Way Ref: JLR-HTG-122809
| Document Owner: | FLANDRE1
| Document Author: | PBEDDOW1
| Date | Change Requested By | Description of Requested Change | Version No: | Change Approved By |  |  |  | Latest References
| 2024-04-12 | Alkaios Lazaris | New APQP Workbook with 44 tasks as per AIAG standard | 1 | Trevor Harkin |  |  |  | 2025-03-20 | Paul Beddow | Update to tab "PCDS V4-new APQP Workbook_V2" - to align with Phase 3 APQP solution Update to tab "APQP Review Summary PCDS V4" - Updated gateway changes to the table and changed content on " Additional Information " | 1.7 | Faye Landreth
| 2024-04-18 | Alkaios Lazaris | No changes to the document-Added properly document to JLR-way page | 1.1 | Trevor Harkin
| 2024-04-22 | Alkaios Lazaris | Corrected typos identified by Jillian Dawson Task 2.13 - "regardless" Task 4.6 - "environmental" | 1.2 | Trevor Harkin
| 2024-11-01 | Paul Beddow | Corrected understanding to Task 3.1 - Description change in column D Supplier has received all packaging requirements and a plan is in place to ensure availability for IPB Build events onwards. Confirm parts will be shipped in production intent packaging for IPB Build Events unless an exception is provided by Logistics Programme Management to Supplier understands packaging stategy for parts (Checklist), Fully understands the process and requirements through supplier guidelines. Understand EU1121 process. A plan is in place to ensure production intent packaging used for TT Build events onwards and E EU1121 Form to EU1121 Form (Attached at 4.6) | 1.3 | Faye Landreth
|  |  | Updated Document Name |  | Faye Landreth
|  |  | Updated Document Owner |  | Faye Landreth
|  |  | Updated Document Author |  | Faye Landreth
| 2024-11-01 | Paul Beddow | Update to CCDS Process Step Ref - included process step names | 1.4 | Faye Landreth
| 2024-11-13 | Paul Beddow | Corrected links to APQP Workbook Summary tab | 1.5 | Faye Landreth
| 2024-11-13 | Paul Beddow | Tracker tab removed (not relevant to CCDS team) | 1.5 | Faye Landreth
| 2025-02-14 | Paul Beddow | Update to task description 3.1a from Prototype Packaging to Buy-off of new special packaging | 1.6 | Faye Landreth
| 2025-03-20 | Paul Beddow | Update to tab "PCDS V4-new APQP Workbook_V2" - to align with Phase 3 APQP solution Update to tab "APQP Review Summary PCDS V4" - Updated gateway changes to the table and changed content on " Additional Information " | 1.7 | Faye Landreth
Printed Copies are Uncontrolled